T-UBT Snapshot for Strategy Group

February 2009

| Location: Fontana | Department: The Busy Module |
| --- | --- |
| Co-Leads: Sam Jones, Labor Kathy Johnson, Mgmt. | Sponsors: Sally Labor Rep, UNAC Michael Smith, Director Dr. Goodcare, PIC |
| Meeting Schedule & Location: | 1st Thursday of each month, 12:30 – 2:30 in the Busy Module Conference Room |
| Charter completed | Team members are in place |
| Yes: X | No: | Yes: X | No: |
| Training Sue & Joe are scheduled for UBTM on 3/19 | _Y__ Co-Lead Training (“How to Co-Lead a Partnership Team”) _N__ UBT-Member Training for Labor team members _Y__ Rapid Improvement Model (RIM) for all team members _Y__ Sufficient LMP process training to do the work of the team |

| Overall Assessment: (add comments, if necessary) Our organizational work is done, & trying to determine what our 1-3 goals should be. Looking for help from our sponsors to prioritize. |  |  | Making progress, growing confidence |
| --- | --- | --- | --- |
|  |  | X | Struggling, but coming together |
|  |  |  | Concerns exist requiring sponsor escalation/intervention |
| Date: 2/06/08 Aim/Goal Statement: Within 30 days, increase the percent of patient beds elevated to 30(in Busy Mod, from 50% to 90%. SAMPLE ONLY | Describe test of change: 2/08/08: Post sign above beds of 2 nurses for 1 day & evaluate results 2/11/08: Post sign above beds of 2 nurses on each shift for 1 week & evaluate results 2/20/08: Post sign above all beds in the Busy Mod, for 2 weeks & measure results 3/15/08: Order & hang permanent signage (branded) for all beds in Busy Mod. | Results: 2/08/08:Nurses said signs would help more if not hidden by equipment – shift signs to left 2/11/08: Elevation of beds was checked 3 times/day during rounding and noted on clipboard. 70% were at 30( 2/20/08: Data collected at rounding shows 86% at 30(. Nurses indicate that it helps. |
| Date: 3/05/08 Aim/Goal Statement: Achieve target of 10 total sick days off per FTE in the Busy Module by year end 2008 SAMPLE ONLY | Describe test of change: 3/05/08: Create bulletin board with all attendance data this year, compared with last year, and engage staff in identifying barriers to improvement | Results: 3/15/08: Bulletin board was created, but there are inconsistencies between dept. and region data for the Busy Module. Waiting for confirmation of accurate data from Attendance. Got feedback from staff to bring to April UBT meeting. |

| Metric Description: Adult Primary Care | Team Target | Team Baseline (if known) | Frequency of Metric Measurement | Performance to date | Comments/ Considerations |
| --- | --- | --- | --- | --- | --- |
| Pt. Care / Service Goal #1 Overall Rate of Care (HCAHPS) | 67% Max. 60.3 Min. | 49.1% (2/08) | HCAHPS Survey Results Summary received Monthly ASQ Monthly <website> | 53.5% | Customer Comments relate largely to rude, uncaring and loud noises |
| Pt. Care / Service Goal #2 |  |  |  |  |  |
| Access Goal (if appropriate) |  |  |  |  |  |
| Attendance: Total Sick Days/FTE (annualized) | 10 | 18.63 (2/08) | Monthly <website> | 17.50 |  |
| Workplace Safety: Accepted Worker’s Comp Claims per 100 FTE | 0 | 3 (in 2007) | Monthly Workplace Injury & Information System (WIIS) | 0 |  |
| Clinical Goal #1 Missed opportun. Diabetic HbA1c Testing | 50% |  |  |  |  |
| Clinical Goal #2 Missed opportun. Diabetic LDL-C Screening | 50% |  |  |  |  |
| Employee Satisfaction & Involvement: P Pulse Q# 5 (Resources to do our jobs) | 60% Favorable | 36% Favorable (2007) | People Pulse annually |  |  |